## Status Report
Project Name: Plant Pals Operations
Today's date: July 5
Summary |  |  |  | Overall Status (RAG)
We have installed new software to keep track of incoming orders and begun sending out the first test batch of Plant Pals to customers. However, we have run into issues with product quality, customer communication, and the delivery process. Our next milestones include sending the test batch customers newsletters on plant upkeep and sending out the second batch of plants. This report also includes top risks and issues that have arisen and how we intend to take action.
Completed Tasks and Milestones
Description | Date | Status | Owner |  | Comments
installed of new software equipment | June 15 | Completed | IT Specialist |  | took three days longer than expected
Began sending test batches of Plant Pals orders to customers | June 21 | Completed | fulfilment director |  | The number of orders exceeded targets by 15%.
Upcoming Tasks and Milestones
Description | Date | Status | Owner |  | Comments
Send the first batch customers e-newsletters on how to take care of their plants. | July 7 | Upcoming | Customer service manager |  | The newsletter must follow Office Green’s brand design guidelines.
hit 95% of delivery dates | July 19 | Upcoming | Fulfillment Director |  | the error rate should be below 5%
Top Risks and Issues
Issue |  | Impact | Action |  |  | Owner
10% of plants werent properly potted |  | Profit loss, complaints, and budget issues | re-evaluate plant potting process |  |  | Warehouse Operations Manager
The customer relations team is receiving only 30% of requests and complaints |  | Customer dissatisfaction | Fix problems with new customer service software |  |  | IT Soecialist
Not enough delivery drivers |  | Customer dissatisfaction - cancel subscriptions | Hire and train more delivery drivers |  |  | HR Specialist