## Template
ROAM Analysis
| Issues | Actions | ROAM Designation
Issue 1 | 10% of plants are not being potted properly. | You contacted the warehouse to update the potting process and have had no issues for two weeks. | Resolved
Issue 2 | Customers are complaining. | Your team reached out to the customers, listened to their issues, and offered to send them a free round of new plants. Most customers were satisfied with this solution. | Owned
Issue 3 | There is a software issue preventing your customer relations team receiving all requests and complaints. | You assign your IT Specialist to fix the problem as soon as possible. | Owned
Issue 4 | Some customers are canceling their subscriptions. | Your team checks in with the customers and, despite offering them a subscription promotion, they still want to cancel. There is nothing you can do, but the impact is minimal. | Accepted
Issue 5 | There are not enough delivery drivers. | You assign your HR Specialist to schedule a hiring day to hire and onboard more drivers. | Owned
Issue 6 | Plants are being delivered late. | Your team reassessed the delivery routes, making them more efficient and minimizing late deliveries. | Mitigated
Issue 7 | Your budget is tightening. | Your Financial Analyst reassessed project spending and was able to increase the budget. The additional money was enough to offset recent losses. | Resolved