## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Project team | Went well | Installation of the tablets | 40% loved the tablet experience
Customers | Went well | tablets ease of use | 22% said the tablet was hard to use - The tablet was glitchy but it might’ve just been our table
Project team | Needs improvement | Table turn time | orders were sent back
Project team | Needs improvement | Technical issues regarding the POS integration process |  | update process manual
Project team | Went well | the weekly calls with vendors helped us stay on track and clarify task dependencies
Customers | Needs improvement | didn’t get many participants for the birthday club | 84% didnt sign up for the birthday club | update the content on the website and the tablets so it’s clearer what the program is, what we’re asking, and how people can participate
Project team | Needs improvement | A few internal operation issues |  | So for the next rollout, we want to do a better job of understanding each location’s history before planning gets underway. That way we can account for things we might need to address ahead of time.
Project team | Needs improvement | Tablet implementation took longer than thought |  | There was some vacation time that was unaccounted for, so this is a good reminder to make sure we plan things properly based on everyone’s availability.
Project team | Needs improvement | lack of understanding between what the front of house staff does and the back of house staff does. |  | share experiences it will help everyone work together more effectively. lok at the waitstaff training process.