## WBS Spreadsheet
Milestone | Task ID | Task | Owner | Duration (days) | Notes
Establish a plant delivery and logistics plan | 1.1 | source materials for packaging | Fulfillment Director
| 1.2 | hire delivery drivers | Human Resources Specialist
| 1.3 | calculating the delivery fees | Financial Analyst
Select and install supply chain software and equipment | 2.1 | supervise vendor setup of inventory management | Inventory Manager
| 2.2 | supervise vendor installation of fulfillment equipment | Inventory Manager
| 2.3 | determine internal safety protocols | Quality Assurance Tester
Develop and launch an employee training program | 3.1 | develop training sessions | Human Resources Specialist
| 3.2 | train employees | Training Manager
| 3.3 | monitor employee progress and improve training processes | Training Manager